## Backlog
WanderWise
Members: | Tasnim Oyshi, Yossef Eini
Task | Description | Member | Status | Start Date | End Date | Comments
Brainstorming & Idea Validation | Discussed potential web-app ideas and finalized WanderWise (AI Trip Planner) as the project topic. | All | Completed | 2025-09-30 | 2025-10-01 | Idea finalized after comparing three proposed app topics; WanderWise selected for feasibility and innovation.
Technology Research & Feasibility Study | Explored Gemini AI, Google Places API, Firebase Auth, and React framework for integration possibilities. | Yossef Eini | Completed | 2025-10-02 | 2025-10-09 | Documented integration flow for Gemini AI, Google Places API, Firebase Auth, and React compatibility. | Researched feasibility and limitations of APIs and AI models.
System Architecture Planning | Outlined frontend (React + Tailwind), backend (Node.js + Firebase), and AI module (Gemini 2.0 Flash). | Tasnim Oyshi | Completed | 2025-10-02 | 2025-10-31 | Architecture mapped out; decided on Vite for fast React setup and Firebase for authentication and data storage.
UI Wireframe & Design Sketch | Created layout mockups for Home, Trip Planner, and My Trips dashboard pages. | Tasnim Oyshi | Completed | 2025-10-13 | 2025-11-03 | Basic wireframes for Home, Trip Planner, and My Trips pages drafted; final layout pending feedback.
Project Setup & Repository Creation | Initialized React project with Vite, set up Tailwind CSS and Firebase; pushed to GitHub and Vercel. | Yossef Eini | Completed | 2025-10-14 | 2025-11-03 | React and Tailwind configured; Firebase initialized; GitHub repo connected with Vercel deployment pipeline.
User Authentication Setup | Implemented Google OAuth login using Firebase Authentication for secure sign-in. | Yossef Eini | Completed | 2025-10-14 | 2025-11-03 | Configured Google OAuth with Firebase; authentication tested successfully in local environment.
Destination Input Form Design | Developed input fields for destination, travel days, budget, and traveler type with state handling. | Yossef Eini | Completed | 2025-10-18 | 2025-11-14 | Created input form for user preferences (destination, days, budget, traveler type); validated field states.
Gemini AI Integration | Connected Gemini 2.0 Flash API to generate day-by-day travel itineraries based on user input. | Tasnim Oyshi | Completed | 2025-10-18 | 2025-11-16 | Successfully linked Gemini 2.0 Flash model; generated JSON itineraries based on dynamic user prompts.
JSON Parsing and Display Logic | Parsed AI response (JSON) to extract hotel, attraction, and schedule data for display. | All | Completed | 2025-10-22 | 2025-11-16 | Parsed AI-generated JSON response; displayed hotels, attractions, and daily schedules in UI.
Google Places API Integration | Fetched real-time hotel and attraction details with photo references and map links. | All | Completed | 2025-10-22 | 2025-11-17 | Integrated Places API to fetch hotel and attraction data; added photo references and live Google Maps links.
Trip Storage with Firebase Firestore | Enabled users to save and retrieve trip plans through personalized dashboards. | All | Completed | 2025-10-22 | 2025-11-20 | Configured Firestore for trip saving; tested user-specific storage retrieval under My Trips page.
Dashboard and My Trips Page Development | Built sections to view trip history, create new plans, and open Google Maps links directly. | All | Completed | 2025-11-05 | 2025-11-21 | Built responsive dashboard for managing and viewing saved trip itineraries.
Error Handling & Placeholder Images | Handled missing or invalid photo references using default images for clean UI. | Yossef Eini | Completed | 2025-11-05 | 2025-11-21 | Implemented default placeholder for missing or invalid images from Google Places API.
Responsive UI & Design Polish | Improved layouts for mobile and tablet devices using Tailwind breakpoints. | Tasnim Oyshi | Completed | 2025-11-05 | 2025-11-24 | Optimized layout for desktop, tablet, and mobile; refined Tailwind breakpoints.
Testing & Debugging | Tested API calls, AI prompt responses, authentication, and data retrieval functions. | Yossef Eini | Completed | 2025-11-06 | 2025-11-24 | Performed integration testing for AI response, API calls, and authentication flow.
Deployment to Vercel | Deployed the web app for public access and verified live integration with Firebase and Gemini. | Yossef Eini | Completed | 2025-11-06 | 2025-11-25 | Successfully deployed to Vercel; verified functionality of Firebase and Gemini APIs in production.
Final UI Polish & Performance Optimization | Refined color scheme, fonts, and loading times for better user experience. | Tasnim Oyshi | Completed | 2025-11-07 | 2025-11-26 | Improved color scheme, font contrast, and page load times; removed redundant API calls.
Presentation Slides & Demo Video Preparation | Created slides and video walkthrough highlighting features and system architecture. | Tasnim Oyshi | Completed | 2025-11-15 | 2025-12-08 | Created final slides and recorded walkthrough demonstrating all key features and architecture.
Final Testing & Submission | Performed last-minute bug fixes, verified project workflow, and submitted final report and code. | Yossef Eini | Completed | 2025-11-16 | 2025-12-12 | Conducted end-to-end testing, fixed minor UI and logic bugs, and submitted report and GitHub repository.

## Read Me
To use the template
1 | Change the document name to "Group num Backlog" (e.g., Group 1 Backlog),
and share it among the members & the instructor (yan.chen01@sjsu.edu)
2 | In Backlog, enter project name and group members
Then document each task as a row:
| 2.1) | Task name (such as Brainstorming, UI Design, etc.)
| 2.2) | Describe the task in more details
| 2.3) | Choose the member who's responsible for the task
| 2.4) | Choose the status
| 2.5) | For started (In Progress) tasks, enter the start date
| 2.6) | For Completed tasks, enter the end date
| 2.7) | Enter any additional notes
3 | Hide or Delete this Read Me Page (or Move it after Backlog so Backlog is the front page)
Color Codes (auto)
Red background: |  | Error
Red text: |  | Urgent task (due soon or blocking other tasks)
Grey text: |  | Completed
The last submission should have NO red background (no error) and all taskes should be in grey (all completed)
Possible Errors
| 2 | Missing group number or group members
| 2.5) | Missing start date for an In Progress or Completed task
OR Having start date for a Not Started task
| 2.6) | Missing end date for a Completed task
OR Having end date for an uncompleted task

## Utils (hidden)
Member | All | Tasnim Oyshi | Yossef Eini